## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Overdue
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Android application to search of work | hosam - batool - thaer | 2022-09-02 | 2022-10-10 |  | 22.22% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | interface of the system | hosam |  | 2020-06-04 | 2020-06-14 | 10 | Complete
| Feature 1 | interface to login | batool |  | 2020-06-04 | 2020-04-08 | 4 | Complete | feature for design the interface system
| Feature 2 | interface to publication a job | thaer |  | 2020-06-08 | 2020-06-13 | 5 | Complete | feature for design the interface system
| Feature 3 | interface choose job | batool |  | 2020-06-10 | 2020-06-14 | 4 | Overdue | feature for design the interface system
| Sprint 2 | Dealing with the database | hosam |  | 2020-06-17 | 2020-06-25 | 8 | In Progress
| Feature 4 | entering user data | thaer |  | 2020-06-17 | 2020-06-18 | 1 | In Progress | feature for database
| Feature 5 | adding new work | batool |  | 2020-06-18 | 2020-06-22 | 4 | Overdue | featurefor database
| Feature 6 | adding new employee | hosam |  | 2020-06-23 | 2020-06-25 | 2 | Not start
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.